## Sheet1
Tentative Schedule of WESP 2018 |  | Legend:
Friday, July 14 2017 | Video Conference I: Discusses broad outline and structure of WESP 2018 and timetable the report | Joint action
Monday, 17 July 2017 | DPAD sends review of key points from video conference for further comment/amendment | DPAD action
Monday, 31 July 2017 | Contributors send outlines of Box proposals - space limits restrict final inputs to 1 box per Commission/Division of a maximum of 600 words | Regional Commission, UNCTAD, FfDO, UNWTO action
Monday, 7 August 2017 | DPAD sends comments on the box outlines to the contributors
Tuesday, 5 September 2017 | DPAD sends preliminary model-based growth forecasts to all contributing partners
Wednesday, 6 September 2017 | Video Conference II: Discuss initial global assumptions, preliminary forecasts and regional developments
Thursday, 7 September 2017 | DPAD sends key points from video conference for further comment/amendment
Monday, 11 September 2017 | Contributors send first drafts of Boxes
Friday, 15 September 2017 | DPAD sends comments on the draft Boxes to the counterparts
Friday, 22 September 2017 | Contributors in UNCTAD and Regional Commissions send remaining draft inputs/bullet points for LINK meeting report (GEO)
Friday, 29 September 2017 | DPAD releases the GEO report for the LINK meeting, and shares with all contributing partners
3-5 October 2017 | LINK Meeting in Geneva: Including meeting with WESP partners to discuss final preparation of WESP 2018
Monday, 9 October 2017 | FfDO sends draft inputs
Friday, 13 October 2017 | Contributors send comments/revisions on GEO report for preparation of WESP 2018, including expanded regional discussions
Monday, 16 October 2017 | Contributors send revised boxes
Friday, 27 October 2017 | DPAD sends full draft of WESP 2018 to UNCTAD, UNWTO, FfDO, Regional Commissions
Friday, 3 November 2017 | Contributors send final comments/revisions on all draft chapters
Friday, 3 November 2017 | DPAD sends first draft of Executive Summary and Annex tables for comment
Friday, 10 November 2017 | Contributors send final comments/revisions on Executive Summary and Annex tables
13-17 November 2017 | DPAD sends final drafts of all Chapters and Executive Summary for clearance, editing and typesetting
Friday, 17 November 2017 | DPAD sends final draft of Executive Summary for translation into other UN official languages.
Friday, 17 November 2017 | DPAD sends first draft of press releases
Wednesday, 22 November 2017 | DPAD finalizes drafts of the press releases
Wednesday, 5 December 2017 | DPAD sends final launch materials
7-12 December 2017 | Global launch of WESP 2018